## Project
Project Engineer | Project year | Order number | Customer | Project | Product | Manufactured by | PO delivery term | Q'ty | Project Value | Max LD | LD Risk | Max LD Amount | Extra cost | Change order | Change order amount | PO Date | PO Delivery Date | Actual shipdate | Balance | Project Phrase | Status | Progress
Project Engineer1 | 2023 | 18210304 | Customer1 | Project1 | Heater | USA | FOB | 3 | 2363614.45 | 0% | No | 0 | 0 | No | 0 | 2023-07-14 | 2024-06-21 | 2025-10-04 | 1654530.115 | Final Document | Shipped | 100%
Project Engineer1 | 2023 | 18210304 | Customer1 | Project1 | Control Panel | USA | FOB | 3 | 0 | 0% | No | 0 | 0 | Yes | 19003 | 2023-07-14 | 2024-06-21 | 2025-09-17 | 0 | Final Document | Shipped | 100%
Project Engineer1 | 2023 | 18291861 | Customer2 | Project2 | Heater | USA | EXW | 1 | 518196.05 | 0% | No | 0 | 0 | No | 0 | 2023-11-14 | 2024-11-12 | 2026-02-15 | 155458.815 | Completed | Shipped | 100%
Project Engineer1 | 2024 | 18407648 | Customer3 | Project3 | Heater | USA | FOB | 4 | 831455 | -5% | Yes | -41572.75 | 0 | No | 0 | 2024-04-22 | 2025-07-07 |  | 249436.5 | Procurement | Delayed | 20%
Project Engineer1 | 2024 | 18492257 | Customer4 | Project4 | Heater | Spain | EXW | 1 | 107400 | -5% | No | 0 | -4475.408 | Yes | 6000 | 2024-08-01 | 2025-03-13 |  | 0 | Shipping | Delayed | 95%
Project Engineer1 | 2024 | 18492257 | Customer4 | Project4 | Control Panel | China | EXW | 1 | 0 | 0% | No | 0 | 0 | Yes | 0 | 2024-08-01 | 2025-03-13 | 2026-06-11 | 0 | Completed | Shipped | 100%
Project Engineer1 | 2025 | 18664359 | Customer4 | Project19 | Heater | Spain | EXW | 1 | 286400 | -5% | No | -14320 | 0 | Yes | 10500 | 2025-04-16 | 2025-11-07 |  | 42960 | Final inspection | Delayed | 80%
Project Engineer1 | 2025 | 18721178 | Customer4 | Project5 | Control Panel | China | EXW | 4 | 368740 | -5% | No | -18437 | 0 | No | 0 | 2025-04-28 | 2026-02-04 |  | 0 | Fabrication | On track | 50%
Project Engineer2 | 2022 | 17939411 | Customer5 | Project6 | Heater | USA | FOB | 4 | 6710454.03 | 0% | No | 0 | 0 | No | 0 | 2022-08-02 | 2023-11-29 |  | 671045.403 | Fabrication | Delayed | 40%
Project Engineer2 | 2022 | 17939411 | Customer5 | Project6 | Control Panel | USA | FOB | 1 | 0 | 0% | No | 0 | 0 | No | 0 | 2022-08-02 | 2023-11-29 | 2025-02-14 | 0 | Final Document | Shipped | 100%
Project Engineer2 | 2023 | 18254957 | Customer6 | Project8 | Heater | USA | FOB |  | 1589287.3 | 0% | No | 0 | 0 | No | 0 | 2023-09-15 | 2024-07-28 |  | 476786.19 | Fabrication | Delayed | 45%
Project Engineer2 | 2023 | 18254957 | Customer6 | Project8 | Control Panel | China | FOB |  | 0 | 0% | No | 0 | 0 | No | 0 | 2023-09-15 | 2024-07-28 | 2025-10-27 | 0 | Final Document | Shipped | 100%
Project Engineer2 | 2023 | 18188317 | Customer7 | Project9 | Heater | USA | FOB | 1 | 4943980 | 0% | No | 0 | 0 | No | 0 | 2023-06-16 | 2024-12-07 |  | 988796 | Fabrication | Delayed | 20%
Project Engineer2 | 2023 | 18188317 | Customer7 | Project9 | Control Panel | China | FOB | 1 | 0 | 0% | No | 0 | 0 | No | 0 | 2023-06-16 | 2024-12-07 | 2025-10-03 | 0 | Final Document | Shipped | 100%
Project Engineer2 | 2023 | 18239263 | Customer8 | Project10 | Heater | USA |  | 7 | 10692464.76 | 0% | No | 0 | 0 | No | 0 | 2023-08-22 | 2025-03-01 | 2026-06-10 | 8553971.808 | Final Document | Shipped | 100%
Project Engineer2 | 2023 | 18239263 | Customer8 | Project10 | Control Panel | China |  | 3 | 0 | 0% | No | 0 | 0 | No | 0 | 2023-08-22 | 2025-03-01 | 2026-06-10 | 0 | Final Document | Shipped | 100%
Project Engineer2 | 2023 | 18239263 | Customer8 | Project10 | Vessel | South Korea |  | 5 | 0 | 0% | No | 0 | 0 | No | 0 | 2023-08-22 | 2025-03-01 | 2026-06-10 | 0 | Final Document | Shipped | 100%
Project Engineer3 | 2023 | 18185328 | Customer9 | Project11 | Heater | USA | EXW | 2 | 311639 | 0% | No | 0 | 0 | No | 0 | 2023-06-09 | 2023-11-29 | 2025-02-04 | 124655.6 | Final Document | Shipped | 100%
Project Engineer3 | 2023 | 18351480 | Customer10 | Project12 | Heater | USA | EWX | 1 | 1079706.52 | 0% | No | 0 | 0 | No | 0 | 2024-02-02 | 2025-01-11 |  | 0 | Fabrication | Delayed | 35%
Project Engineer3 | 2024 | 18649372 | Customer11 | Project13 | Heater | Spain | EWX | 2 | 370530 | 0% | No | 0 | 0 | No | 0 | 2025-03-18 | 2025-10-21 |  | 74106 | Fabrication | On track | 45%
Project Engineer3 | 2024 | 18649372 | Customer11 | Project13 | Control Panel | China | EWX | 2 | 0 | 0% | No | 0 | 0 | No | 0 | 2025-03-18 | 2025-10-21 |  | 0 | Fabrication | On track | 50%
Project Engineer3 | 2025 | 18793810 | Customer13 | Project15 | Heater | USA | FCA | 1 | 1509175.85 | -10% |  | -150917.585 | 0 | No | 0 | 2025-09-27 | 2026-09-29 |  | 0 | Prepare document | On track | 10%
Project Engineer3 | 2025 | 18793810 | Customer13 | Project15 | Heater | USA | FCA | 1 | 0 | 0% | No | 0 | 0 | No | 0 | 2025-09-27 | 2026-09-29 |  | 0 | Prepare document | On track | 10%
Project Engineer3 | 2025 | 18793810 | Customer13 | Project15 | Control Panel | USA | FCA | 1 | 0 | 0% | No | 0 | 0 | No | 0 | 2025-09-27 | 2026-09-29 |  | 0 | Prepare document | On track | 10%
Project Engineer3 | 2025 | 18793810 | Customer13 | Project15 | Control Panel | USA | FCA | 1 | 0 | 0% | No | 0 | 0 | No | 0 | 2025-09-27 | 2026-09-29 |  | 0 | Prepare document | On track | 10%
Project Engineer1 | 2025 | 18768883 | Customer14 | Project16 | Heater | USA | EWX | 1 | 841776.14 | -5% |  | -42088.807 | 0 | No | 0 | 2025-09-05 | 2027-02-12 |  | 0 | Prepare document | On track | 10%
Project Engineer1 | 2025 | 18800831 | Customer4 | Project17 | Heater | Spain | EWX | 1 | 257437.8 | -5% |  | -12871.89 | 0 | No | 0 | 2025-10-29 | 2026-06-02 |  | 0 | Prepare document | On track | 10%
Project Engineer1 | 2025 | 18800831 | Customer4 | Project17 | Control Panel | China | EWX | 1 | 0 | 0% | No | 0 | 0 | No | 0 | 2025-10-29 | 2026-06-02 |  | 0 | Prepare document | On track | 10%

## Invoice
Project year | SEQ | Project Engineer | Sale order No. | Customer | Total amount | Percentage of amount | Invoice value | Currency unit | Invoice plan date | Invoice Issued Date | Invoice due date | Plan payment date | Expected Payment date | Actual Payment received date | Actual Delayed | Received value | Payment Status
2023 | 1 | Project Engineer1 | 18210304 | Customer1 | 2363614.45 | 40% | 945445.78 | USD | 2024-12-13 | 2024-12-13 | 60 | 2025-02-11 | 2025-02-11 | 2025-03-04 | 21 | 945445.78 | Paid
2023 | 2 | Project Engineer1 | 18210304 | Customer1 |  | 30% | 709084.335 | USD | 2025-09-06 | 2025-05-14 | 60 | 2025-11-05 | 2025-07-13 | 2025-07-25 | 12 | 709084.335 | Paid
2023 | 3 | Project Engineer1 | 18210304 | Customer1 |  | 30% | 709084.335 | USD | 2025-12-07 | 2025-08-08 | 60 | 2026-02-05 | 2025-10-07 |  | 55 | 0 | Invoiced
2024 | 1 | Project Engineer3 | 18649372 | Customer11 | 370530 | 20% | 74106 | USD | 2025-04-15 | 2025-03-06 | 30 | 2025-05-15 | 2025-04-05 | 2025-03-18 | -18 | 74106 | Paid
2024 | 2 | Project Engineer3 | 18649372 | Customer11 |  | 20% | 74106 | USD | 2025-08-02 | 2025-05-13 | 30 | 2025-09-01 | 2025-06-12 |  | 172 | 0 | Aging
2024 | 3 | Project Engineer3 | 18649372 | Customer11 |  | 20% | 74106 | USD | 2025-09-09 | 2025-06-16 | 30 | 2025-10-09 | 2025-07-16 |  | 138 | 0 | Aging
2024 | 4 | Project Engineer3 | 18649372 | Customer11 |  | 35% | 129685.5 | USD | 2025-10-21 |  | 30 | 2025-11-20 |  |  |  | 0 | Not invoiced
2024 | 5 | Project Engineer3 | 18649372 | Customer11 |  | 5% | 18526.5 | USD | 2025-12-07 |  | 30 | 2026-01-06 |  |  |  | 0 | Not invoiced
2025 | 1 | Project Engineer3 | 18793810 | Customer13 | 1509175.85 | 10% | 150917.585 | USD | 2026-03-27 |  | 30 | 2026-04-26 |  |  |  | 0 | Not invoiced
2025 | 2 | Project Engineer3 | 18793810 | Customer13 |  | 20% | 301835.17 | USD | 2026-05-06 |  | 30 | 2026-06-05 |  |  |  | 0 | Not invoiced
2025 | 3 | Project Engineer3 | 18793810 | Customer13 |  | 10% | 150917.585 | USD | 2026-06-15 |  | 30 | 2026-07-15 |  |  |  | 0 | Not invoiced
2025 | 4 | Project Engineer3 | 18793810 | Customer13 |  | 50% | 754587.925 | USD | 2026-07-25 |  | 30 | 2026-08-24 |  |  |  | 0 | Not invoiced
2025 | 5 | Project Engineer3 | 18793810 | Customer13 |  | 10% | 150917.585 | USD | 2026-06-22 |  | 30 | 2026-07-22 |  |  |  | 0 | Not invoiced
2025 | 1 | Project Engineer1 | 18768883 | Customer14 | 841776.14 | 15% | 126266.421 | USD | 2025-11-07 | 2025-07-25 | 30 | 2025-12-07 | 2025-08-24 |  | 99 | 0 | Aging
2025 | 2 | Project Engineer1 | 18768883 | Customer14 |  | 35% | 294621.649 | USD | 2026-06-10 |  | 30 | 2026-07-10 |  |  |  | 0 | Not invoiced
2025 | 3 | Project Engineer1 | 18768883 | Customer14 |  | 50% | 420888.07 | USD | 2027-02-12 |  | 30 | 2027-03-14 |  |  |  | 0 | Not invoiced
2023 | 1 | Project Engineer3 | 18185328 | Customer9 | 311639 | 40% | 124655.6 | USD | 2025-03-24 | 2025-03-11 | 30 | 2025-04-23 | 2025-04-10 | 2025-02-15 | -54 | 124655.6 | Paid
2023 | 2 | Project Engineer3 | 18185328 | Customer9 |  | 60% | 186983.4 | USD | 2024-08-07 |  | 30 | 2024-09-06 |  |  |  | 0 | Not invoiced
2023 | 1 | Project Engineer3 | 18351480 | Customer10 | 1079706.52 | 30% | 323911.956 | USD | 2025-06-28 | 2025-04-02 | 30 | 2025-07-28 | 2025-05-02 |  | 213 | 0 | Aging
2023 | 2 | Project Engineer3 | 18351480 | Customer10 |  | 50% | 539853.26 | USD | 2025-11-05 |  | 30 | 2025-12-05 |  |  |  | 0 | Not invoiced
2023 | 3 | Project Engineer3 | 18351480 | Customer10 |  | 20% | 215941.304 | USD | 2025-11-22 |  | 30 | 2025-12-22 |  |  |  | 0 | Not invoiced
2023 | 1 | Project Engineer1 | 18291861 | Customer2 | 518196.05 | 30% | 155458.815 | USD | 2025-08-21 | 2025-05-14 | 30 | 2025-09-20 | 2025-06-13 | 2025-06-09 | -4 | 155458.815 | Paid
2023 | 2 | Project Engineer1 | 18291861 | Customer2 |  | 70% | 362737.235 | USD | 2025-11-06 | 2025-08-08 | 30 | 2025-12-06 | 2025-09-07 |  | 85 | 0 | Invoiced
2023 | 1 | Project Engineer2 | 18254957 | Customer6 | 1589287.3 | 10% | 158928.73 | USD | 2024-12-23 | 2025-01-07 | 45 | 2025-02-06 | 2025-02-21 | 2024-12-19 | -64 | 158928.73 | Paid
2023 | 2 | Project Engineer2 | 18254957 | Customer6 |  | 20% | 317857.46 | USD | 2024-12-29 | 2025-01-17 | 45 | 2025-02-12 | 2025-03-03 | 2025-01-22 | -40 | 317857.46 | Paid
2023 | 3 | Project Engineer2 | 18254957 | Customer6 |  | 60% | 953572.38 | USD | 2025-09-27 |  | 45 | 2025-11-11 |  |  |  | 0 | Not invoiced
2023 | 4 | Project Engineer2 | 18254957 | Customer6 |  | 10% | 158928.73 | USD | 2025-10-19 |  | 45 | 2025-12-03 |  |  |  | 0 | Not invoiced
2022 | 1 | Project Engineer2 | 17939411 | Customer5 | 6710454.03 | 10% | 671045.403 | USD | 2024-12-24 | 2024-10-28 | 45 | 2025-02-07 | 2024-12-12 | 2025-04-05 | 114 | 671045.403 | Paid
2022 | 2 | Project Engineer2 | 17939411 | Customer5 |  | 25% | 1677613.5075 | USD | 2025-08-07 | 2025-06-16 | 45 | 2025-09-21 | 2025-07-31 |  | 123 | 0 | Aging
2022 | 3 | Project Engineer2 | 17939411 | Customer5 |  | 55% | 3690749.7165 | USD | 2026-02-21 |  | 45 | 2026-04-07 |  |  |  | 0 | Not invoiced
2022 | 4 | Project Engineer2 | 17939411 | Customer5 |  | 10% | 671045.403 | USD | 2026-04-08 |  | 45 | 2026-05-23 |  |  |  | 0 | Not invoiced
2023 | 1 | Project Engineer2 | 18188317 | Customer7 | 4943980 | 20% | 988796 | USD | 2024-08-07 | 2025-04-30 | 30 | 2024-09-06 | 2025-05-30 | 2025-04-19 | -41 | 988796 | Paid
2023 | 2 | Project Engineer2 | 18188317 | Customer7 |  | 20% | 988796 | USD | 2025-09-22 |  | 30 | 2025-10-22 |  |  |  | 0 | Aging
2023 | 3 | Project Engineer2 | 18188317 | Customer7 |  | 50% | 2471990 | USD | 2025-12-19 |  | 30 | 2026-01-18 |  |  |  | 0 | Not invoiced
2023 | 4 | Project Engineer2 | 18188317 | Customer7 |  | 10% | 494398 | USD | 2026-02-01 |  | 30 | 2026-03-03 |  |  |  | 0 | Not invoiced
2023 | 1 | Project Engineer2 | 18239263 | Customer8 | 10692464.76 | 5% | 534623.238 | USD | 2025-08-07 | 2025-06-16 | 45 | 2025-09-21 | 2025-07-31 |  | 123 | 0 | Aging
2023 | 2 | Project Engineer2 | 18239263 | Customer8 |  | 10% | 1069246.476 | USD | 2025-07-13 | 2025-04-02 | 45 | 2025-08-27 | 2025-05-17 | 2025-04-12 | -35 | 1069246.476 | Paid
2023 | 3 | Project Engineer2 | 18239263 | Customer8 |  | 10% | 1069246.476 | USD | 2025-04-14 | 2025-01-23 | 45 | 2025-05-29 | 2025-03-09 | 2025-02-06 | -31 | 1069246.476 | Paid
2023 | 4 | Project Engineer2 | 18239263 | Customer8 |  | 20% | 2138492.952 | USD | 2025-04-14 | 2025-01-23 | 45 | 2025-05-29 | 2025-03-09 | 2025-02-06 | -31 | 2138492.952 | Paid
2023 | 5 | Project Engineer2 | 18239263 | Customer8 |  | 30% | 3207739.428 | USD | 2025-04-14 | 2025-01-23 | 45 | 2025-05-29 | 2025-03-09 | 2025-02-06 | -31 | 3207739.428 | Paid
2023 | 6 | Project Engineer2 | 18239263 | Customer8 |  | 10% | 1069246.476 | USD | 2025-04-14 | 2025-01-23 | 45 | 2025-05-29 | 2025-03-09 | 2025-02-06 | -31 | 1069246.476 | Paid
2023 | 7 | Project Engineer2 | 18239263 | Customer8 |  | 5% | 534623.238 | USD | 2025-08-31 | 2025-05-27 | 45 | 2025-10-15 | 2025-07-11 |  | 143 | 0 | Aging
2023 | 8 | Project Engineer2 | 18239263 | Customer8 |  | 10% | 1069246.476 | USD | 2025-10-02 |  | 45 | 2025-11-16 |  |  |  | 0 | Not invoiced
2024 | 1 | Project Engineer1 | 18407648 | Customer3 | 831455 | 30% | 249436.5 | USD | 2025-07-07 | 2024-03-27 | 30 | 2025-08-06 | 2024-04-26 | 2025-04-24 | 363 | 249436.5 | Paid
2024 | 2 | Project Engineer1 | 18407648 | Customer3 |  | 50% | 415727.5 | USD | 2025-11-06 |  | 30 | 2025-12-06 |  |  |  | 0 | Not invoiced
2024 | 3 | Project Engineer1 | 18407648 | Customer3 |  | 20% | 166291 | USD | 2025-12-07 |  | 30 | 2026-01-06 |  |  |  | 0 | Not invoiced
2024 | 1 | Project Engineer1 | 18492257 | Customer4 | 107400 | 50% | 53700 | USD | 2025-08-22 | 2025-05-14 | 30 | 2025-09-21 | 2025-06-13 |  | 171 | 0 | Aging
2024 | 2 | Project Engineer1 | 18492257 | Customer4 |  | 50% | 53700 | USD | 2025-11-06 | 2025-07-24 | 30 | 2025-12-06 | 2025-08-23 |  | 100 | 0 | Invoiced
2025 | 1 | Project Engineer1 | 18664359 | Customer4 | 286400 | 15% | 42960 | USD | 2025-08-07 | 2025-05-15 | 30 | 2025-09-06 | 2025-06-14 | 2025-07-23 | 39 | 42960 | Paid
2025 | 2 | Project Engineer1 | 18664359 | Customer4 |  | 35% | 100240 | USD | 2025-11-06 | 2025-07-24 | 30 | 2025-12-06 | 2025-08-23 |  | 100 | 0 | Aging
2025 | 3 | Project Engineer1 | 18664359 | Customer4 |  | 50% | 143200 | USD | 2025-11-14 |  | 30 | 2025-12-14 |  |  |  | 0 | Not invoiced
2025 | 1 | Project Engineer1 | 18721178 | Customer4 | 368740 | 15% | 55311 | USD | 2025-08-20 | 2025-05-14 | 30 | 2025-09-19 | 2025-06-13 |  | 171 | 0 | Invoiced
2025 | 2 | Project Engineer1 | 18721178 | Customer4 |  | 35% | 129059 | USD | 2025-11-18 |  | 30 | 2025-12-18 |  |  |  | 0 | Not invoiced
2025 | 3 | Project Engineer1 | 18721178 | Customer4 |  | 50% | 184370 | USD | 2026-02-04 |  | 30 | 2026-03-06 |  |  |  | 0 | Not invoiced
2025 | 1 | Project Engineer1 | 18800831 | Customer4 | 257437.8 | 15% | 38615.67 | USD | 2025-10-22 |  | 30 | 2025-11-21 |  |  |  | 0 | Not invoiced
2025 | 2 | Project Engineer1 | 18800831 | Customer4 |  | 35% | 90103.23 | USD | 2026-02-15 |  | 30 | 2026-03-17 |  |  |  | 0 | Not invoiced
2025 | 3 | Project Engineer1 | 18800831 | Customer4 |  | 50% | 128718.9 | USD | 2026-02-23 |  | 30 | 2026-03-25 |  |  |  | 0 | Not invoiced